## Sheet1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Sprint Review
As a user, I can view shapes. | Task 1: Initialize QT project. | Nik | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
As an administrator, I can add and remove shapes. | Task 2: Create Shape base class. | Ziyang | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Task 3: Create Vector class. | Basel | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Task 4: Create Shape subclasses | Ziyang | In Progress | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40
| Task 5: Write user stories | Nik, Basel, Ali, Ziyang, Bryson | Closed | 20 | 20 | 15 | 5 | 0 | 0 | 0 | 0
|  |  | Total | 110 | 110 | 105 | 95 | 90 | 90 | 90 | 90
Sprint Goal
Initialize project, create simple UI, make significant progress on back-end code.