## Sheet1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Sprint Review
As a user, I can view shapes. | Task 1: Initialize QT project. | Nik | Complete | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0
As an administrator, I can add and remove shapes. | Task 2: Create Shape base class. | Ziyang, Ye | Complete | 20 | 20 | 20 | 20 | 20 | 10 | 0 | 0
As an administrator, I can move and modify shapes. | Task 3: Create Vector class. | Basel | Complete | 20 | 20 | 10 | 0 | 0 | 0 | 0 | 0
As a user, I can view testimonials. | Task 4: Create Shape subclasses | Ziyang, Ye | In Progress | 40 | 40 | 40 | 40 | 40 | 30 | 20 | 20
As a user, I can add a testimonial. | Task 5: Create project ui. | Nik | Complete | 30 | 30 | 30 | 15 | 0 | 0 | 0 | 0
As a user, I can view the company’s contact information. | Task 6: Create add shape dialog with options | Nik | Complete | 30 | 30 | 30 | 30 | 30 | 15 | 0 | 0
As a user, I can attempt to log into the administrative console. | Task 7: Create Sign in dialog | Bryson | Complete | 20 | 30 | 30 | 30 | 30 | 20 | 0 | 0
As a user, I can view a shape report of all shapes sorted by id. | Task 8. Implement draw shape functionality. | Nik | In Progress | 30 | 30 | 30 | 30 | 30 | 30 | 20 | 15
As a user, I can view a shape report of all shapes sorted by Area. | Task 9: Add shape parser. | Basel, Ali | In Progress | 40 | 40 | 40 | 40 | 40 | 35 | 30 | 30
As a user, I can view a shape report of all shapes with a perimeter sorted by perimeter. | Task 10: Add testimonial class | Basel, Ali | In Progress | 10 | 10 | 10 | 10 | 10 | 8 | 8 | 8
| Task 11: Add testimonial parser | Basel, Ali | In Progress | 20 | 10 | 10 | 10 | 10 | 8 | 8 | 8
| Task 12: Add report ui | Nik | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Task 13: Add report by shape id | Unassigned | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Task 14: Add report by shape perimeter | Unassigned | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Task 15: Add report by shape area | Unassigned | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Task 16: Add testimonial ui | Nik | In Progress | 10 | 10 | 10 | 6 | 6 | 6 | 6 | 6
| Task 17: Add testimonial functiionality | Unassigned | In Progress | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Task 18: Add contact us dialog | Unassigned | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Sprint Goal
Complete project! Complete UI, Complete parser logic, add shape report functionality. |  |  | Total | 355 | 355 | 345 | 306 | 291 | 237 | 167 | 162